## Lead
Project Name - E Medicare System
Group Number - 1
Team Lead & Frontend Lead-Harini Kandasami & Dhaneshan S
Backend Lead - Pradeepa S

## Status Track
Project Status Check Repositoryrt Team - 1
Sl no. | Employee ID | Name | Domain | Module | 2022-03-22 | 2022-03-23 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-27
1 | 2528422 | Dhivyabharathi D | Unit Testing | Admin, Medicine,Contact us Unit Testing | Group and Project Discussion | Admin,Medicine | Contact us | Team discussion about Frontend and Backend connections | PPT-Technology Used | Demo and error rectification
2 | 2529352 | Pradeepa S | Backend | Medicine module | Group and Project Discussion | Entity | Service, Controller | Team discussion about Frontend and Backend connections | PPT-Environmental setup | Demo and error rectification
3 | 2528874 | Sherlin X | Unit Testing | User, Cart Unit Testing | Group and Project Discussion | User testing | Cart | Team discussion about Frontend and Backend connections | PPT-Output | Demo and error rectification
4 | 2529073 | Anuchitra C | Backend | Cart module | Group and Project Discussion | Entity | Service, Controller | Team discussion about Frontend and Backend connections | PPT-Proposed | Demo and error rectification
5 | 2529179 | Abhiram K V | Database | Database Repository | Group and Project Discussion | Repository creation | Service, Controller | Team discussion about Frontend and Backend connections | PPT-Introduction | Demo and error rectification
6 | 2529059 | M Prasanth | Frontend | User,Cart,Billing Frontend | Group and Project Discussion | Html,Css,Bootstrap | Angular | Team discussion about Frontend and Backend connections | PPT-Conclusion | Demo and error rectification
7 | 2529069 | R Deepak Kumar | Frontend | Style layout, Home and About us | Group and Project Discussion | Html,Css | Bootstrap,Angular | Team discussion about Frontend and Backend connections | PPT-Advantages | Demo and error rectification
8 | 2527997 | Dhaneshan S | Frontend | Admin,Medicine,Contact us Frontend | Group and Project Discussion | Html,Css,Bootstrap | Postman and Angular. | Team discussion about Frontend and Backend connections | PPT-Modules | Demo and error rectification
9 | 2529099 | Sonu Patidar | Backend | User module Backend | Group and Project Discussion | Entity | Service, Controller | Team discussion about Frontend and Backend connections | PPT-Future scope and references | Demo and error rectification
10 | 2530684 | Harini Kandasami | Backend | Admin module Backend | Group and Project Discussion | Entity | Service, Controller | Team discussion about Frontend and Backend connections | PPT-Abstract,Team members,content,Abstract | Demo and error rectification

## Status Meeting
Status Meeting Group - E Medicare System
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-10-21 | -- | -- | 12:30 | -- | 6:00 | --
2022-10-22 | 10:30 | a | 1:00 | a | 6:20 | a
2022-10-23 | 11:00 | a | 2:00 | a | 5:10 | a
2022-10-24 | 10:45 | a | 3:00 | a | 5:30 | a
2022-10-25 | 10:10 | a | 1:30 | a | 6:30 | a
2022-10-26 | 9:30 | a | 3:30 | a | 7:30 | a