## Lead
Project Name - E Medicare System
Group Number - 1
Team Lead -Harini Kandasami
Frontend Lead - Dhaneshan S
Backend Lead - Pradeepa S

## Status Track
Project Status Check Repository Team - 1
Sl no. | Employee ID | Name | Domain | Module | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26
1 | 2530684 | Harini Kandasami | Frontend,Backend & Testing | Conctact Us & Medicine Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Abstract,Team members,content,Abstract
2 | 2529352 | Pradeepa S | Frontend,Backend & Testing | Medicine Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Environmental setup
3 | 2527997 | Dhaneshan S | Frontend,Backend & Testing | User Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Modules
4 | 2529073 | Anuchitra C | Frontend,Backend & Testing | Medicine Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Proposed
5 | 2529179 | Abhiram K V | Frontend,Backend & Testing | User Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Introduction
6 | 2529059 | M Prasanth | Frontend,Backend & Testing | Admin Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Conclusion
7 | 2529069 | R Deepak Kumar | Frontend,Backend & Testing | Cart Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Advantages
8 | 2528422 | Dhivyabharathi D | Frontend,Backend & Testing | Medicine Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Technology Used
9 | 2529099 | Sonu Patidar | Frontend,Backend & Testing | Cart Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Future scope and references
10 | 2528874 | Sherlin X | Frontend,Backend & Testing | Admin Module | Group and Project Discussion | Entity,Repository | Service, Controller | Frontend | Frontend-Backend Connection &Demo | PPT-Output

## Status Check Meets
Status Meeting Group - E Medicare System
| Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
| 2022-10-21 | -- | -- | 12:30 | P | 6:00 | P
| 2022-10-22 | 10:30 | P | 1:00 | P | 4:40 | P
| 2022-10-23 | 11:00 | P | 2:40 | P | 7:10 | P
| 2022-10-24 | 10:45 | P | 3:00 | P | 6:45 | P
| 2022-10-25 | 10:10 | P | 1:30 | P | 5:50 | P
| 2022-10-26 | 10:00 | P | 2:15 | P | 7:00 | P
| 2022-10-27 | 9:40 | P | 3:00 | P | 6:30 | P